## ProjectCategories (12)
Project_Number | Lot_Number | Address | Category_Number | Category_Description | Percent_Complete | Budgeted | Disbursed | Balance
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 4 | DISBURSING FEE | 100 | 65000 | 65000 | 0
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 1460 | LAND | 100 | 1216260.8 | 1216260.8 | 0
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 4631 | ARCHITECTURAL | 80 | 50000 | 38354.5 | 11645.5
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 6191 | ENGINEERING | 100 | 139843.12 | 139843.12 | 0
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 9189 | BUILDING PERMITS | 10 | 500000 | 38712 | 461288
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 13624 | GENERAL LIABILITY INSURANCE | 10 | 55000 | 5131.29 | 49868.71
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 14652 | BUILDERS RISK INSURANCE | 0 | 45000 | 0 | 45000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 15463 | CONTINGENCY | 20 | 993396.08 | 183151 | 810245.08
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 35070 | RENTAL MARKETING | 0 | 50000 | 0 | 50000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 38902 | INTEREST | 0 | 1000000 | 0 | 1000000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 39263 | OFFICE MGMT | 0 | 150000 | 0 | 150000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 52035 | ATTORNEY FEES | 100 | 35500 | 35500 | 0
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 89425 | DEMO | 100 | 23000 | 22370 | 630
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90099 | GENERAL CONSTRUCTION | 0 | 1700000 | 0 | 1700000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90100 | HAULING | 0 | 100000 | 0 | 100000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90101 | EXCAVATION, GRADING | 25 | 1500000 | 313461 | 1186539
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90102 | FOOTINGS & FOUNDATION | 0 | 914000 | 0 | 914000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90103 | CONCRETE SLAB / WALKWAY | 0 | 731000 | 0 | 731000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90105 | ASPHALT/STRIPE | 0 | 275000 | 0 | 275000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90106 | RETAINING WALLS | 10 | 175000 | 10875 | 164125
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90107 | IRRIGATION SYSTEM | 0 | 70000 | 0 | 70000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90108 | LUMBER/ROOF TRUSSES | 0 | 1583000 | 0 | 1583000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90109 | MISC MATERIALS | 0 | 125000 | 0 | 125000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90110 | PLUMBING | 0 | 1650000 | 0 | 1650000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90111 | HVAC | 0 | 815000 | 9000 | 806000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90112 | ELECTRICAL | 0 | 2145000 | 0 | 2145000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90113 | ELECTRICAL FIXTURES | 0 | 60000 | 0 | 60000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90114 | CARPENTRY LABOR | 0 | 1780000 | 0 | 1780000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90115 | CRAIN, BOBCAT | 0 | 150000 | 0 | 150000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90116 | ROOFING SHINGLES | 0 | 245000 | 0 | 245000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90117 | GUTTERS / DOWNSPOUTS | 0 | 30000 | 0 | 30000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90118 | SIDING, EXT TRIM, SHUTTERS | 0 | 420000 | 0 | 420000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90119 | METAL RAILINGS, TRASH ENCLOSURES | 0 | 141000 | 0 | 141000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90120 | CONCRETE LIGHT WEIGHT | 0 | 114000 | 0 | 114000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90121 | FIRE SUPPRESSION | 0 | 601000 | 0 | 601000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90122 | INSULATION | 0 | 326000 | 0 | 326000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90123 | FIRE ALARM | 0 | 55000 | 0 | 55000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90124 | WINDOWS, GLASS DOORS | 0 | 228000 | 0 | 228000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90126 | DRYWALL | 0 | 1250000 | 0 | 1250000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90127 | PAINTING | 0 | 445000 | 0 | 445000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90129 | CABINETS & TOPS | 0 | 589000 | 0 | 589000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90130 | BASE, TRIM, NAILS | 0 | 20000 | 0 | 20000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90131 | INTERIOR DOOR, METAL DOORS | 0 | 275000 | 0 | 275000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90132 | METAL ENTRY DOORS | 0 | 85000 | 0 | 85000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90133 | UNIT/CARPORT # PLACKETS | 0 | 20000 | 0 | 20000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90134 | APPLIANCES | 0 | 360000 | 0 | 360000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90135 | SHELVING, MIRRORS, SHOWER DOORS | 0 | 185000 | 0 | 185000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90136 | INTERIOR FLOORING | 0 | 400000 | 75000 | 325000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90138 | BLINDS | 0 | 30000 | 0 | 30000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90139 | FITNESS CENTER | 0 | 100000 | 0 | 100000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90140 | COMMON LABOR | 10 | 525000 | 37413 | 487587
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90141 | TRASH REMOVAL | 0 | 75000 | 13526 | 61474
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90142 | PORTABLE TOILET | 0 | 15000 | 0 | 15000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90144 | TEMP ELECTRIC | 0 | 15000 | 0 | 15000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90145 | FINAL CLEAN | 0 | 50000 | 0 | 50000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90146 | FINISH GRADE | 0 | 60000 | 5000 | 55000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 90147 | SWIMMING POOL, GAZEBO | 0 | 225000 | 0 | 225000
260021 | 1 | (C) 5926 OLD STATE ROAD, IMPERIAL, MO 63052 | 97463 | TRASH ENCLOSURES | 0 | 20000 | 0 | 20000
[6 empty] | 25000000 | 2208597.71 | 22791402.29